## Project Plan
Task # | Parent Task | Title | Description | Status | Priority | Assigned To | Start Date | Duration Estimate | Time Spent (Hours) | End Date | Start Date Constraint | Notes
1 | Planning | Team Assignment | Assigns students to teams | Done | High | All | 2022-09-23 | 10 minutes | 10 minutes | 2022-09-26 | N/A
2 | Planning -> Team Assignment | Project Proposal | Create a rough plan for a project | Done | High | All | 2022-09-23 | 1 hour | 1 hour | 2022-09-26 | N/A
3 | Planning -> Project Proposal | Propose Project | Submit project proposal to the professor | Done | High | All | 2022-09-26 | 1 hours | 0 hours | 2022-09-26 | 2022-09-23
4 | Planning -> Propose Project | Get Project Approval | Get project proposal approval from professor | Done | High | All | 2022-09-26 | 0 hours | 0 hours | 2022-09-26 | 2022-09-26
5 | Planning -> Project Approval | Create Project Plan | Create an outline of tasks that must be completed for the project | In Progress | High | All | 2022-10-06 | 3 hours | 2 hours | 2022-10-06 | 2022-09-26
6 | Planning | Role Assignment | Assign students to invididual roles for the assignment | Done | High | All | 2022-10-06 | 15 minutes | 15 minutes | 2022-10-06 | N/A
7 | Planning -> Project Plan | Select Development Methodology | Decide what project methodology the team will use | Not Started | Normal | All | Undecided | 15 minutes | None yet | N/A | N/A
8 | Planning -> Project Plan | Feasibility Study | Assess whether the project plan is feasibile within the allotted timeframe | Not Started | High | All | Undecided | 30 minutes | None yet | N/A | N/A
9 | Analysis | Requirements From Existing System | Look at existing examples to decide what requirements ours will have | Not Started | Normal | All | Undecided | 15 minutes | None yet | N/A | N/A
10 | Analysis | Use Cases/User Stories | Decide what use cases that the project has | Not Started | Normal | All | Undecided | 10 minues | None yet | N/A | N/A
11 | Analysis | Data Requirements | Establish the process used to identify, prioritize, precisely, formulate, and validate the data required | Not Started | Normal | All | Undecided | 30 minutes | None yet | N/A | N/A
12 | Analysis | Common Requirements | Decide the screens, menus, navigation, workflow, login, user types, audit tracking, archiving, and configuration that are required of the system | Not Started | Normal | All | Undecided | 20 minutes | None yet | N/A | N/A
13 | Analysis | Interface Requirements | Decide the requirements needed for the user interface | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
14 | Analysis | Implementation Requirements | Features required to transition to a new system | Not Started | Normal | All | Undecided | 15 minutes | None yet | N/A | N/A
15 | Analysis | Prioritize Requirements (MoSCoW) | Decide what requirements must, should, could, or won't be done | Not Started | Normal | All | Undecided | 15 minutes | None yet | N/A | N/A
16 | Analysis | Check Requirements | Double check all of the requirements prior to submission and categorize | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
17 | Analysis -> Check Requirements | Clear | Requirements must be clear and concise | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
18 | Analysis -> Check Requirements | Unambiguous | The requirements must be written in a way so that they can only be interpretted in one manner | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
19 | Analysis -> Check Requirements | Consistent | Requirements must be consistent with one another | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
20 | Analysis -> Check Requirements | Prioritized | Prioritize exactly what requirements have higher priority incase we must cut them out | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
21 | Analysis -> Check Requirements | Verifiable | Requirements must be limited and precisely defined | Not Started | Normal | All | Undecided | 10 minutes | None yet | N/A | N/A
22 | Analysis -> All Requirements Completed | Validation and Verification of Requirements | Review of requirements to make sure we haven't missed any or created overlapping requirements | Not Started | Normal | All | Undecided | 11 minutes | None yet | N/A | N/A
23 | Analysis -> Validation and Verification of Requirements | Submit Requirements for Approval | Submit requirements to professor | Not Started | High | All | Undecided | 0 minutes | None yet | N/A | N/A
24 | Analysis -> Requirement Submission | Sign Off On Requirements | Get approval from Professor | Not Started | High | All | Undecided | 0 minutes | None yet | N/A | N/A
25 | Design | Drawing a maze to the screen | Design our maze generation | Not Started | High | Jason/Matthew | Undecided | 1 hour | None yet | N/A | N/A
26 | Design | User Interface Design | Decide a user interface | Not Started | Normal | Jason/Matthew | Undecided | 30 minutes | None yet | N/A | N/A
27 | Design | Choose Agent AI | Deside the machine learning algorithm that our agent will run off of | Not Started | High | John/Teddy | Undecided | 1 hour | None yet | N/A | N/A
28 | Design | Displaying Agents | How will we display our agents | Not Started | High | John/Teddy | Undecided | 20 minutes | None yet | N/A | N/A
29 | Design -> Displaying Agnets | Agent Movement | Decide agent movement rules | Not Started | High | John/Teddy | Undecided | 20 minutes | None yet | N/A | N/A
30 | Design | Logging Agent Data | Which data will need to be tracked | Not Started | High | John/Teddy | Undecided | 15 minutes | None yet | N/A | N/A
31 | Design -> Logging Agent Data | Calculating Fitness | Decide and design vectors for surviving agents | Not Started | High | John/Teddy | Undecided | 45 minutes | None yet | N/A | N/A
32 | Design -> Calculating Fitness | Agent Training | Decide data regarding epochs | Not Started | High | John/Teddy | Undecided | 30 minutes | None yet | N/A | N/A
33 | Design | Low-Level Design | Decide the more intricate portions of the design of the program | Not Started | Normal | All | Undecided | 2 hours | None yet | N/A | N/A
34 | Implementation | Setup Development Environment | Setup the group's developemnt environment | Not Started | High | All | Undecided | 30 minutes | None yet | N/A | N/A
35 | Implementation | Version Control Setup | Setup the group's version control software for the environment | Not Started | High | All | Undecided | 1 hour | None yet | N/A | N/A
36 | Implementation | Bug Tracking | Set up the group's bug tracking method | Not Started | Low | All | Undecided | 20 minutes | None yet | N/A | N/A
37 | Implementation | User Interface | Implement a user interface | Not Started | High | Jason/Matthew | Undecided | 2 hours | None yet | N/A | N/A
38 | Implementation | Maze Creation | Create and draw maze to a screen | Not Started | High | Jason/Matthew | Undecided | 4 hours | None yet | N/A | N/A
39 | Implementation | Generating Agents to Screen | Create our agents in our maze | Not Started | High | John/Teddy | Undecided | 30 minutes | None yet | N/A | N/A
40 | Implementation | Create Agent AI | Implement the machine learning algorithm that our agent will run off of | Not Started | High | John/Teddy | Undecided | 4 hours | None yet | N/A | N/A
42 | Implementation -> Create Agent AI | Implement Movement | Move the displayed agents corresponding to their discovery movement | Not Started | High | John/Teddy | Undecided | 3 hours | None yet | N/A | N/A
43 | Implementation -> Create Agent AI | Agent Training | Implement the code that mutates the AI between runthroughs of the maze | Not Started | High | John/Teddy | Undecided | 3 hours | None yet | N/A | N/A
44 | Testing | User Interface Testing | Test the UI for bugs, ease of use, and readibilty | Not Started | Normal | Jason/Matthew + Volunteers | Undecided | 2 hours | None yet | N/A | N/A
45 | Testing | Map Design Testing | Test the maze generation to make sure it always has a solution and has no other problems | Not Started | Normal | All | Undecided | 2 hours | None yet | N/A | N/A
46 | Testing | Agent Testing | Test displayed agents for correct actions | Not Started | Normal | All | Undecided | 2 hours | None yet | N/A | N/A
47 | Testing -> Agent Testing | Agent Development Testing | Test agent training cycles | Not Started | Normal | John/Teddy | Undecided | 2 hours | None yet | N/A | N/A
48 | Testing -> Agent Testing | Agent Data Collection Testing | Verify collected agent data | Not Started | Normal | John/Teddy | Undecided | 2 hours | None yet | N/A | N/A
49 | Testing | Automated Testing | Create a form of automated testing | Not Started | Low | John/Teddy | Undecided | 4 hours | None yet | N/A | N/A
50 | Deployment | Deployment Plan | Execute our project's deployment | Not Started | Normal | All | Undecided | 30 minutes | None yet | N/A | N/A
51 | Maintenance | Roadmap | Plan the future of the project | Not Started | Normal | All | Undecided | 20 minutes | None yet | N/A | N/A
52 | Maintenance | Will a Next Version be Released? | Will there be a next version? | Not Started | Low | All | Undecided | 10 minutes | None yet | N/A | N/A
53 | Maintenance | Time Resources Devoted to Maintenance? | How long will maintenance take? | Not Started | Low | All | Undecided | 10 minutes | None yet | N/A | N/A
54 | Maintenance | Who is Assigned to Maintenance? | Who is assigned to maintenance? | Not Started | Low | All | Undecided | 10 minutes | None yet | N/A | N/A
55 | Wrap-Up | Lessons Learned | Discuss what was learned | Not Started | Normal | All | Undecided | 15 minutes | None yet | N/A | N/A
56 | Wrap-Up | Next Steps | Discuss any remaining project steps | Not Started | Normal | All | Undecided | 30 minutes | None yet | N/A | N/A
57 | Wrap-Up | Peer Review | Conduct a peer review | Not Started | High | All | Undecided | 1 hour | None yet | N/A | N/A

## Team Roles
Team Members | Team Roles
John | Sponsor
Matthew | Project Lead
Teddy | Technical Lead
Jason | Analysist